Implementation Backlog

Clinic-Specific AI Dental Screening — Academic Prototype

Revised for: Solo, 4th-Year Capstone Project

Constraints: Free-tier infrastructure only · ~4 week timeline

Volume 5 of 5 — Implementation Backlog (Revised)

# Scope Note

Note: The original backlog had ~240 tasks across 16 sprints for a funded team over 12 weeks. This revision cuts it to ~70 tasks a single student can realistically complete in ~4 weeks (roughly 12–15 hrs/week), on entirely free infrastructure. Tasks unsuitable for AI-agent automation are marked accordingly.

# Timeline Overview

| Week | Focus | Approx. Tasks |
| --- | --- | --- |
| 0 (Prework) | Accounts, dataset download, environment setup | 6 |
| 1 | Auth, Patient & Visit CRUD | 18 |
| 2 | Image upload + AI model training/integration | 18 |
| 3 | Dentist review UI, PDF report, (stretch) Grad-CAM | 16 |
| 4 | Testing, deploy, polish, write-up | 12 |

# Prework (Before Coding — Do These First)

| ID | Task | Est. | Depends On | Acceptance |
| --- | --- | --- | --- | --- |
| PW1 | Create free accounts: MongoDB Atlas, Cloudinary, Vercel, Render/Railway, GitHub, Google Colab/Kaggle | 2h | — | All credentials saved in a local .env (not committed) |
| PW2 | Download chosen dataset (Zenodo caries) and sanity-check image/label counts | 1h | — | Image count matches label count; no zero-byte files |
| PW3 | Set up repo: frontend/, backend/, ai_model/, docs/ folders; .gitignore for datasets/env files | 1h | — | Clean repo pushed to GitHub |
| PW4 | Write CLAUDE.md (use Volume 0 as the template) in repo root | 1h | PW3 | File exists with stack/style/branch rules |
| PW5 | Confirm Colab/Kaggle GPU access works (run a 1-epoch smoke-test train) | 1h | PW2 | Training loop runs without error for 1 epoch |
| PW6 — Human task | Read through the dataset license (CC BY) and note attribution requirement for your final report | 15m | — | Cannot be automated — a citation/attribution decision |

# Week 1: Auth, Patient & Visit CRUD

| ID | Task | Est. | Depends On | Acceptance |
| --- | --- | --- | --- | --- |
| T101 | Init Next.js (TS, Tailwind, App Router) in /frontend | 1h | PW3 | npm run dev serves a blank page |
| T102 | Init FastAPI project in /backend with app/ module layout | 1h | PW3 | uvicorn app.main:app runs; /health returns 200 |
| T103 | Connect backend to MongoDB Atlas | 1h | PW1,T102 | Connection succeeds on startup |
| T104 | User model/schema + password hashing (passlib/bcrypt) | 1h | T103 | Password never stored in plaintext |
| T105 | POST /auth/login issuing JWT in httpOnly cookie | 2h | T104 | Valid creds → cookie set; invalid → 401 |
| T106 | Role-check dependency (dentist/receptionist/admin) | 1h | T105 | Wrong-role request → 403 |
| T107 | Seed script to create first admin user | 30m | T104 | python scripts/create_admin.py works |
| T108 | Frontend login page + cookie-based auth flow | 2h | T105 | Login redirects to dashboard on success |
| T109 | Protect frontend routes (redirect to /login if unauthenticated) | 1h | T108 | Direct nav to /patients while logged out redirects |
| T110 | Patient model/schema (Pydantic + Mongo) | 30m | T103 | Schema validates required fields |
| T111 | Patient CRUD endpoints (GET/POST/PUT/DELETE, soft-delete) | 3h | T110 | All 5 operations return correct status codes |
| T112 | Frontend Patient List page (table + search) | 3h | T111 | Lists patients; search filters client-side |
| T113 | Frontend Add/Edit Patient forms | 3h | T111 | Create and update both persist to backend |
| T114 | Visit model/schema + CRUD endpoints under /patients/{id}/visits | 3h | T111 | Visit created/listed/updated correctly |
| T115 | Frontend Visit list (on patient profile) + New Visit form | 3h | T114 | New visit appears in patient's timeline |
| T116 | Basic pytest coverage for auth + patient + visit endpoints | 2h | T111,T114 | Core happy-paths covered |
| T117 | Role restrictions on patient/visit routes (dentist/receptionist only) | 1h | T106,T111 | Admin-only or wrong-role calls rejected |
| T118 | Commit + push week 1 milestone | 15m | T101–T117 | main branch builds and runs locally |

# Week 2: Image Upload + AI Integration

| ID | Task | Est. | Depends On | Acceptance |
| --- | --- | --- | --- | --- |
| T201 | Configure Cloudinary SDK in backend | 30m | PW1 | Test upload succeeds via SDK |
| T202 | POST /visits/{id}/images endpoint (multipart upload → Cloudinary URL) | 2h | T201,T114 | Returns image URL, stored on visit |
| T203 | Frontend image upload component + preview | 2h | T202 | Selecting a file uploads and shows thumbnail |
| T204 | Validate uploads (JPEG/PNG only, <5MB) | 30m | T202 | Oversized/wrong-type file rejected with clear error |
| T205 | Train YOLOv8n on Colab (checkpointed) using chosen dataset | 4h (mostly unattended) | PW5 | best.pt produced; mAP50 recorded |
| T206 | Run model.val() and record metrics honestly in docs/AI_Results.md | 1h | T205 | Metrics documented, not assumed |
| T207 | Download best.pt into backend/ai_model/weights/ | 15m | T205 | File present in repo (or Git LFS/Drive link if large) |
| T208 | Load YOLO model once at FastAPI startup | 1h | T207 | Model loads without reloading per-request |
| T209 | POST /images/{id}/predict endpoint (runs inference, returns JSON boxes/labels/confidence) | 2h | T208 | Returns well-formed prediction JSON |
| T210 | Map YOLO class indices to disease names | 30m | T209 | Response uses strings not numeric IDs |
| T211 | Predictions model/schema + save to Mongo | 1h | T209 | Each prediction persisted, linked to image |
| T212 | Auto-trigger inference right after upload | 1h | T202,T209 | Upload response includes/triggers prediction |
| T213 | Frontend: display top prediction on visit page | 1h | T211 | Label + confidence shown after upload |
| T214 | Frontend: AI Review page listing all detected boxes | 3h | T211 | All predictions for an image listed clearly |
| T215 | Strip EXIF metadata from uploaded images (piexif) | 1h | T202 | Uploaded images have no EXIF/location data |
| T216 | Basic inference logging (timestamp, latency, count) | 30m | T209 | Log line written per prediction call |
| T217 | Unit test: sample image → expected JSON shape | 1h | T209 | Test passes on a known sample |
| T218 | Commit + push week 2 milestone | 15m | T201–T217 | main branch builds and runs locally |

# Week 3: Dentist Review, PDF Report, (Stretch) Grad-CAM

| ID | Task | Est. | Depends On | Acceptance |
| --- | --- | --- | --- | --- |
| T301 | Correction model/schema + POST /corrections endpoint | 1h | T211 | Correction saved with old/new label |
| T302 | Frontend Dentist Correction UI (approve or relabel dropdown) | 3h | T301,T214 | Dentist can approve or change each label |
| T303 | Mark prediction as reviewed/validated on correction | 1h | T301 | Prediction status updates correctly |
| T304 | Choose PDF library (ReportLab) + design a 1-page template | 1h | — | Template sketch in docs/ |
| T305 | Backend report generator: patient/visit info + findings + image | 3h | T304,T211 | generate_report(visit_id) produces valid PDF |
| T306 | GET /visits/{id}/report endpoint | 1h | T305 | Browser can download the PDF |
| T307 | Frontend “Download Report” button | 30m | T306 | Click triggers file download |
| T308 — Stretch | Research crop-and-classify Grad-CAM approach | 2h | T211 | Written plan or working snippet; time-boxed |
| T309 — Stretch | Implement Grad-CAM heatmap for one class | 3h | T308 | Heatmap image produced for a sample crop |
| T310 — Stretch | Frontend heatmap overlay toggle | 2h | T309 | Toggle shows/hides heatmap on the image |
| T311 | Dashboard page (simple: total patients, total visits, recent activity) | 2h | T111,T114 | 3 summary numbers load from API |
| T312 | Responsive pass on core pages (tablet width) | 2h | All prior UI tasks | No broken layout at 768px width |
| T313 | Accessibility pass (labels, focus order, contrast check) | 1h | All prior UI tasks | Keyboard-only nav works on core flows |
| T314 | pytest coverage for corrections + report endpoints | 1h | T301,T306 | Core happy-paths covered |
| T315 | UI error/success toasts wired to key actions | 1h | T203,T302,T307 | User gets feedback on success/failure |
| T316 | Commit + push week 3 milestone | 15m | T301–T315 | main branch builds and runs locally |

# Week 4: Testing, Deployment, Write-Up

| ID | Task | Est. | Depends On | Acceptance |
| --- | --- | --- | --- | --- |
| T401 | Fix bugs found from a full manual run-through of the whole flow | 3h | All prior | End-to-end flow works without errors |
| T402 | Deploy backend to Render/Railway (free tier); set env vars | 2h | All backend tasks | Public backend URL responds to /health |
| T403 | Deploy frontend to Vercel; point at deployed backend URL | 1h | T402 | Public frontend URL loads and can log in |
| T404 | Verify Cloudinary + Atlas work correctly against deployed instance | 1h | T402,T403 | Upload/predict/report work end-to-end in prod |
| T405 | Basic GitHub Actions: lint + pytest on push (optional but easy credit) | 1h | — | CI badge passes on main |
| T406 | README: setup instructions, stack, how to run locally and where it's deployed | 1h | — | A stranger could clone and run it |
| T407 | docs/AI_Results.md: dataset used, model, actual metrics achieved, limitations | 1h | T206 | Honest, specific numbers — not copied targets |
| T408 | docs/Future_Work.md: everything explicitly deferred (see Volumes 1 & 4 §10) | 30m | — | Clear list for the report's limitations section |
| T409 | Record a short demo video/screenshots for submission | 1h | T404 | Demo shows upload → prediction → correction → report |
| T410 | Final pass: remove dead code, confirm .env.example is current | 1h | — | No secrets committed; example file accurate |
| T411 | Tag v1.0 release on GitHub | 15m | T401–T410 | Release tag exists matching submitted code |
| T412 | Proofread and assemble final written report (using Volumes 0–4 as source material) | 3h | All | Report submitted |

# Tasks Unsuitable for AI-Agent Automation

- PW6 — Reading/understanding the dataset's license terms and deciding on attribution wording.

- T206/T407 — Honestly interpreting and reporting your actual model metrics (an AI agent can compute them, but the honest write-up/interpretation is your judgment call, not something to let an agent embellish).

- T412 — Final report writing — an agent can draft sections, but the assembled narrative, chosen emphasis, and academic voice should be yours.

- Any decision about what counts as “good enough” accuracy for your demo — that's a judgment call for you and your supervisor, not something to automate.

# Example Task Prompt Format (for Claude Code / an AI agent)

“Implement T111: Patient CRUD endpoints. Per Volume 1 §6, build GET/POST/PUT/DELETE /api/patients using FastAPI + the Patient Pydantic schema from T110. Use soft-delete (isDeleted flag), not a hard delete. Return 201 on create, 200 on read/update, 204 on delete, 404 if not found. After generating code, run pytest and confirm T116's tests pass, then commit with message 'T111: patient CRUD endpoints'.”